PROJECT DOCUMENT CONTROL PROCEDURE

50 MW Solar PV Plant with 20 MWh BESS  —  VoltSun Labs (RJ Corp Group)

| Document No. | Revision | Effective Date | Page |
| --- | --- | --- | --- |
| VSL-SLR-PMT-PRC-0035 | 0 | 14-May-2026 | 1 of 6 |

| Prepared By | Reviewed By | Approved By |
| --- | --- | --- |
| [Your Name] Document Controller | PMO Lead | Project Head |

# 1. Purpose & Scope

This procedure defines how project and engineering documentation is created, numbered, reviewed, approved, distributed, and archived across the 50 MW Solar PV plant with 20 MWh BESS project executed by VoltSun Labs. It applies to all engineering drawings, technical specifications, contracts, correspondence, regulatory and quality records, and project management documents generated or received during the project lifecycle.

It applies to all project personnel, discipline engineers, the PMO, subcontractors, and the client/consultant, wherever they originate or receive project documentation.

# 2. Roles & Responsibilities (RACI)

The table below defines who originates, reviews, approves, and receives each major category of project documentation.

| Document Type | Originator | Reviewer | Approver | Distribution |
| --- | --- | --- | --- | --- |
| Engineering Drawings | Design Engineer | Discipline Lead | Project Head | Site Team, Client |
| Technical Specifications | Discipline Lead | QA/QC Manager | Project Head | Procurement, Client |
| HSE Plans & Procedures | HSE Manager | Project Head | Client / PMO | All Site Personnel |
| Inspection & Test Plans | QA/QC Engineer | Discipline Lead | QA/QC Manager | Site QC, Client |
| Contracts & Correspondence | PMO | Project Head | Project Head | PMO, Legal (if applicable) |
| Progress Reports | Document Controller | PMO Lead | Project Head | PMO, Client |

## 2.1 Document Controller Responsibilities

- Maintain the Master Document Register (MDR) and ensure it reflects the current status of every document.

- Issue and log all transmittals, tracking response due dates and following up on overdue items.

- Enforce the numbering convention and revision control rules defined in this procedure.

- Provide weekly/monthly document status reports to the Project Head and PMO.

- Maintain the Document Management System (DMS) — folder structure, access permissions, and version history.

- Archive superseded and as-built documents per the retention policy in Section 6.

# 3. Document Numbering Convention

Every project document is assigned a unique number in the following format:

VSL-SLR-<DISCIPLINE>-<DOC TYPE>-<SEQUENCE>

| Segment | Description |
| --- | --- |
| VSL | Project owner code (VoltSun Labs) |
| SLR | Project / site code (Solar + BESS site) |
| Discipline | 3-letter discipline code, e.g. CIV, ELE, MEC, INC, HSE, QAC, PRO, PMT |
| Doc Type | 3-4 letter document type code, e.g. DRG (Drawing), SPEC (Specification), RPT (Report), PLN (Plan), PRC (Procedure) |
| Sequence | 4-digit running number, unique per document across the project |

Example: VSL-SLR-ELE-DRG-0008 refers to VoltSun Labs, Solar/BESS project, Electrical discipline, Drawing type, sequence number 0008.

# 4. Revision Control Rules

Documents move through the status codes below as they progress from first issue to closeout. Draft revisions prior to formal issue use letters (A, B, C…); once issued for construction, revisions switch to numbers (0, 1, 2…).

| Code | Status | Definition |
| --- | --- | --- |
| IFR | Issued for Review | Circulated internally or to discipline leads for technical review prior to formal submission. |
| IFA | Issued for Approval | Formally submitted to client/consultant/PMO for approval. |
| IFC | Issued for Construction | Approved and released to site for execution; no further changes without a new revision. |
| AFC | Approved for Construction | Confirms client/consultant sign-off; used interchangeably with IFC depending on project terminology. |
| AB | As-Built | Final closeout revision reflecting actual constructed/installed condition. |
| REJ | Returned with Comments | Reviewer has returned the document with comments; originator must revise and resubmit. |

## 4.1 Revision Rules

- Every re-issue of a document, however minor, receives a new revision identifier — no document is ever overwritten without a revision change.

- A superseded revision is archived, never deleted, and remains traceable in the MDR revision history.

- Only the Document Controller can assign the next revision identifier in the MDR, to prevent duplicate or skipped revisions.

- Comments from a review cycle must be closed out (accepted or responded to) before a document can move to IFC/AFC status.

- As-built (AB) status is assigned only after site confirmation that the document reflects actual constructed/installed condition.

# 5. Transmittal Process

All formal document exchange between VoltSun Labs, the client/consultant, and subcontractors is done via numbered transmittals — never by informal email attachment alone. This ensures every submission and approval has a traceable record.

- Originator completes the document and notifies the Document Controller that it is ready for issue.

- Document Controller verifies the document number, revision, and formatting against this procedure.

- Document Controller raises a transmittal (see Transmittal Log template) referencing the document number(s), purpose (For Review / For Approval / For Information / For Construction), and response due date.

- Recipient reviews and returns comments, or approves, within the stated response period.

- Document Controller logs the response in the MDR and closes the transmittal, or raises a follow-up if overdue.

- Where comments are received, the originator revises the document and the cycle repeats under a new revision.

# 6. Filing, Retention & Document Management System

All controlled documents are stored in the project Document Management System (DMS), organized by discipline and document type, mirroring the numbering convention in Section 3. Working/draft files are kept separate from issued/controlled copies.

- Only the current approved revision of a document is held in the active DMS folder; superseded revisions move to a dedicated Archive folder.

- Engineering drawings and IFC/AFC documents are retained for the full project lifecycle plus the defined warranty/defect liability period.

- Regulatory, quality, and HSE records are retained per applicable statutory and contractual requirements, whichever is longer.

- Access permissions in the DMS follow the Distribution Matrix in Section 7 — read/write access is restricted by role.

# 7. Distribution Matrix

Access to project documentation is governed by role, as follows:

| Stakeholder | Access Level | Method |
| --- | --- | --- |
| Project Head | Full access — all disciplines | DMS / SharePoint |
| Discipline Leads | Full access — own discipline, read-only others | DMS / SharePoint |
| Site / Construction Team | IFC and AFC documents only | Transmittal + DMS |
| Client / Consultant | Documents issued for their review/approval | Formal Transmittal |
| PMO | Full access — reporting and audit | DMS / SharePoint |
| Procurement | Specifications and BOQs relevant to open packages | DMS + Email Transmittal |

# 8. Reporting to Project Head & PMO

The Document Controller issues a document status report on a weekly (or as agreed) basis, summarizing:

- Total documents by status (IFR / IFA / IFC / AFC / AB / REJ)

- Documents overdue for review or approval, with ageing

- Open transmittals and pending responses

- Upcoming document submissions per the project schedule

This report is generated directly from the Master Document Register and its accompanying Dashboard, ensuring the Project Head and PMO always work from a single, current source of truth.