## MDR
MASTER DOCUMENT REGISTER
Project: 50 MW Solar PV Plant with 20 MWh BESS ¦ VoltSun Labs (RJ Corp Group) ¦ Doc Controller: [Your Name]
Register updated as of: 21-Aug-2026
S.No | Document No. | Document Title | Discipline | Doc Type | Rev | Status | Originator | Reviewer / Approver | Issue Date | Due Date | Transmittal Ref | Remarks
1 | VSL-SLR-CIV-DRG-0001 | Site Grading & Levelling Plan | Civil | Layout Drawing | 0 | AFC | R. Iyer (Civil) | Discipline Lead - Civil | 2026-05-05 | 2026-05-18 | TR-0001
2 | VSL-SLR-CIV-DRG-0002 | Module Table Foundation Layout | Civil | Layout Drawing | 0 | IFC | N. Verma (Civil) | Discipline Lead - Electrical | 2026-05-09 | 2026-05-25 | TR-0001
3 | VSL-SLR-CIV-DRG-0003 | Pile Foundation Design - Zone A | Civil | Foundation Design | C | IFA | S. Khan (Civil) | Discipline Lead - Mechanical | 2026-05-13 | 2026-06-01 | TR-0001
4 | VSL-SLR-CIV-DRG-0004 | Inverter/BESS Plinth Foundation Design | Civil | Foundation Design | A | IFR | P. Reddy (Civil) | QA/QC Manager | 2026-05-17 | 2026-06-08 | TR-0002 | Overdue - follow up with reviewer
5 | VSL-SLR-CIV-RPT-0005 | Soil Investigation Report | Civil | Report | 1 | AB | D. Bose (Civil) | HSE Manager | 2026-05-21 | 2026-05-31 | TR-0002 | Closed out - construction complete
6 | VSL-SLR-CIV-DRG-0006 | Internal Road & Drainage Layout | Civil | Road Layout | B | REJ | M. Nair (Civil) | PMO | 2026-05-25 | 2026-06-07 | TR-0002 | Comments received from client - resubmission pending
7 | VSL-SLR-CIV-BOQ-0007 | Civil Works BOQ - Zone A & B | Civil | Bill of Quantities | 0 | IFC | A. Sharma (Civil) | Client Consultant | 2026-05-29 | 2026-06-14 | TR-0003
8 | VSL-SLR-ELE-DRG-0008 | Plant Single Line Diagram (SLD) | Electrical | Single Line Diagram | 0 | AFC | R. Iyer (Electrical) | Project Head | 2026-06-02 | 2026-06-21 | TR-0003
9 | VSL-SLR-ELE-DRG-0009 | MV Cable Schedule - Zone A | Electrical | Cable Schedule | C | IFA | N. Verma (Electrical) | Discipline Lead - Civil | 2026-06-06 | 2026-06-28 | TR-0003
10 | VSL-SLR-ELE-DRG-0010 | Earthing & Lightning Protection Layout | Electrical | Layout Drawing | 0 | IFC | S. Khan (Electrical) | Discipline Lead - Electrical | 2026-06-10 | 2026-06-20 | TR-0004
11 | VSL-SLR-ELE-DRG-0011 | DC Cable Routing Layout | Electrical | Layout Drawing | 0 | AFC | P. Reddy (Electrical) | Discipline Lead - Mechanical | 2026-06-14 | 2026-06-27 | TR-0004
12 | VSL-SLR-ELE-DRG-0012 | Inverter Room Electrical Schematic | Electrical | Schematic | 0 | IFC | D. Bose (Electrical) | QA/QC Manager | 2026-06-18 | 2026-07-04 | TR-0004
13 | VSL-SLR-ELE-SPEC-0013 | 33kV Switchgear Technical Specification | Electrical | Specification | C | IFA | M. Nair (Electrical) | HSE Manager | 2026-06-22 | 2026-07-11 | TR-0005
14 | VSL-SLR-ELE-DRG-0014 | BESS Container SLD | Electrical | Single Line Diagram | A | IFR | A. Sharma (Electrical) | PMO | 2026-06-26 | 2026-07-18 | TR-0005 | Overdue - follow up with reviewer
15 | VSL-SLR-ELE-CALC-0015 | Voltage Drop & Cable Sizing Calculation | Electrical | Design Calculation | 1 | AB | R. Iyer (Electrical) | Client Consultant | 2026-06-30 | 2026-07-10 | TR-0005 | Closed out - construction complete
16 | VSL-SLR-MEC-DRG-0016 | Module Mounting Structure - GA Drawing | Mechanical | GA Drawing | B | REJ | N. Verma (Mechanical) | Project Head | 2026-07-04 | 2026-07-17 | TR-0006 | Comments received from client - resubmission pending
17 | VSL-SLR-MEC-CALC-0017 | Wind Load & Structural Calculation | Mechanical | Design Calculation | 0 | IFC | S. Khan (Mechanical) | Discipline Lead - Civil | 2026-07-08 | 2026-07-24 | TR-0006
18 | VSL-SLR-MEC-SPEC-0018 | Tracker Mounting Structure Specification | Mechanical | Specification | 0 | AFC | P. Reddy (Mechanical) | Discipline Lead - Electrical | 2026-07-12 | 2026-07-31 | TR-0006
19 | VSL-SLR-MEC-DRG-0019 | BESS HVAC & Fire Suppression P&ID | Mechanical | P&ID | C | IFA | D. Bose (Mechanical) | Discipline Lead - Mechanical | 2026-07-16 | 2026-08-07 | TR-0007
20 | VSL-SLR-INC-DRG-0020 | SCADA Network Architecture Diagram | Instrumentation & Control | Architecture Diagram | 0 | IFC | M. Nair (Instrumentation & Control) | QA/QC Manager | 2026-07-20 | 2026-07-30 | TR-0007
21 | VSL-SLR-INC-SPEC-0021 | Weather Station Instrumentation Spec | Instrumentation & Control | Specification | 0 | AFC | A. Sharma (Instrumentation & Control) | HSE Manager | 2026-07-24 | 2026-08-06 | TR-0007
22 | VSL-SLR-INC-DRG-0022 | PLC I/O List - Inverter Station | Instrumentation & Control | I/O List | 0 | IFC | R. Iyer (Instrumentation & Control) | PMO | 2026-07-28 | 2026-08-13 | TR-0008
23 | VSL-SLR-HSE-PLN-0023 | Project HSE Management Plan | HSE | Plan | C | IFA | N. Verma (HSE) | Client Consultant | 2026-05-03 | 2026-05-22 | TR-0008
24 | VSL-SLR-HSE-PLN-0024 | Emergency Response & Evacuation Plan | HSE | Plan | A | IFR | S. Khan (HSE) | Project Head | 2026-05-07 | 2026-05-29 | TR-0008 | Overdue - follow up with reviewer
25 | VSL-SLR-HSE-PRC-0025 | Working at Height Procedure | HSE | Procedure | 1 | AB | P. Reddy (HSE) | Discipline Lead - Civil | 2026-05-11 | 2026-05-21 | TR-0009 | Closed out - construction complete
26 | VSL-SLR-HSE-PRC-0026 | Lifting & Rigging Safety Procedure | HSE | Procedure | B | REJ | D. Bose (HSE) | Discipline Lead - Electrical | 2026-05-15 | 2026-05-28 | TR-0009 | Comments received from client - resubmission pending
27 | VSL-SLR-QAC-PLN-0027 | Project Quality Assurance Plan | QA/QC | Plan | 0 | IFC | M. Nair (QA/QC) | Discipline Lead - Mechanical | 2026-05-19 | 2026-06-04 | TR-0009
28 | VSL-SLR-QAC-ITP-0028 | ITP - Module Mounting Structure | QA/QC | Inspection Test Plan | 0 | AFC | A. Sharma (QA/QC) | QA/QC Manager | 2026-05-23 | 2026-06-11 | TR-0010
29 | VSL-SLR-QAC-ITP-0029 | ITP - Cable Laying & Termination | QA/QC | Inspection Test Plan | C | IFA | R. Iyer (QA/QC) | HSE Manager | 2026-05-27 | 2026-06-18 | TR-0010
30 | VSL-SLR-QAC-RPT-0030 | Factory Acceptance Test Report - Inverters | QA/QC | Report | 0 | IFC | N. Verma (QA/QC) | PMO | 2026-05-31 | 2026-06-10 | TR-0010
31 | VSL-SLR-PRO-BOQ-0031 | Procurement BOQ - Electrical Package | Procurement | Bill of Quantities | 0 | AFC | S. Khan (Procurement) | Client Consultant | 2026-06-04 | 2026-06-17 | TR-0011
32 | VSL-SLR-PRO-SPEC-0032 | Module Supply Technical Specification | Procurement | Specification | 0 | IFC | P. Reddy (Procurement) | Project Head | 2026-06-08 | 2026-06-24 | TR-0011
33 | VSL-SLR-PRO-SPEC-0033 | BESS Container Technical Specification | Procurement | Specification | C | IFA | D. Bose (Procurement) | Discipline Lead - Civil | 2026-06-12 | 2026-07-01 | TR-0011
34 | VSL-SLR-PMT-PLN-0034 | Project Execution Plan | Project Management | Plan | A | IFR | M. Nair (Project Management) | Discipline Lead - Electrical | 2026-06-16 | 2026-07-08 | TR-0012 | Overdue - follow up with reviewer
35 | VSL-SLR-PMT-PLN-0035 | Project Schedule (Level 3) | Project Management | Plan | 1 | AB | A. Sharma (Project Management) | Discipline Lead - Mechanical | 2026-06-20 | 2026-06-30 | TR-0012 | Closed out - construction complete
36 | VSL-SLR-PMT-PRC-0036 | Document Control Procedure | Project Management | Procedure | B | REJ | R. Iyer (Project Management) | QA/QC Manager | 2026-06-24 | 2026-07-07 | TR-0012 | Comments received from client - resubmission pending
37 | VSL-SLR-PMT-RPT-0037 | Monthly Progress Report - Template | Project Management | Report | 0 | IFC | N. Verma (Project Management) | HSE Manager | 2026-06-28 | 2026-07-14 | TR-0013

## Dashboard
DOCUMENT STATUS DASHBOARD
Live summary — pulls automatically from the MDR sheet
Total Documents |  | 37
Approved (AFC/AB) |  | 11
Open for Review/Approval |  | 11
Overdue (past due date, not closed) |  | 26
Status Breakdown
Status Code | Meaning | Count
IFR | Issued for Review | 4
IFA | Issued for Approval | 7
IFC | Issued for Construction | 11
AFC | Approved for Construction | 7
AB | As-Built | 4
REJ | Returned with Comments | 4
Documents by Discipline
Discipline | Count
Civil | 7
Electrical | 8
Mechanical | 4
Instrumentation & Control | 3
HSE | 4
QA/QC | 4
Procurement | 3
Project Management | 4

## Revision History (Sample)
REVISION HISTORY — SAMPLE DOCUMENTS
Detailed revision trail for 5 documents, showing how each revision was tracked from first issue to closeout
Document No. | Document Title | Rev | Status | Date | Issued By | Description of Change
VSL-SLR-ELE-DRG-0008 | Plant Single Line Diagram (SLD) | A | Issued for Review | 05-May-26 | R. Iyer | First issue for internal review
|  | B | Returned with Comments | 12-May-26 | Discipline Lead - Electrical | Comments on transformer tap settings
|  | C | Issued for Approval | 20-May-26 | R. Iyer | Comments incorporated, sent for client approval
|  | 0 | Issued for Construction | 02-Jun-26 | PMO | Approved by client, released for construction
VSL-SLR-CIV-DRG-0003 | Pile Foundation Design - Zone A | A | Issued for Review | 08-May-26 | A. Sharma | First issue based on preliminary soil report
|  | B | Returned with Comments | 15-May-26 | Discipline Lead - Civil | Revise pile depth per updated soil data
|  | 0 | Issued for Construction | 28-May-26 | A. Sharma | Finalized after soil report update, IFC released
|  | 1 | As-Built | 10-Aug-26 | A. Sharma | Updated to reflect actual founded levels
VSL-SLR-MEC-DRG-0016 | Module Mounting Structure - GA Drawing | A | Issued for Review | 10-May-26 | N. Verma | Initial structural GA for review
|  | 0 | Issued for Construction | 24-May-26 | N. Verma | No comments received, released for construction
|  | 1 | As-Built | 15-Aug-26 | N. Verma | As-built markup after site installation
VSL-SLR-INC-DRG-0020 | SCADA Network Architecture Diagram | A | Issued for Review | 18-May-26 | S. Khan | First draft for IT/OT review
|  | B | Returned with Comments | 25-May-26 | PMO | Add redundant fiber ring per cybersecurity review
|  | C | Issued for Approval | 02-Jun-26 | S. Khan | Redundancy added, sent for approval
|  | 0 | Issued for Construction | 10-Jun-26 | Client Consultant | Approved, released for construction
VSL-SLR-PMT-PRC-0035 | Document Control Procedure | A | Issued for Review | 01-May-26 | [Your Name] | Initial draft of DC procedure for project
|  | 0 | Approved for Construction | 14-May-26 | Project Head | Approved and issued as project-wide procedure

## Legend & Numbering Convention
LEGEND & DOCUMENT NUMBERING CONVENTION
Numbering Format
VSL-SLR-<DISCIPLINE>-<DOC TYPE>-<SEQUENCE>
Example: VSL-SLR-ELE-DRG-0008 = VoltSun Labs, Solar project, Electrical discipline, Drawing, sequence 0008
Segment | Meaning
VSL | Project owner code — VoltSun Labs
SLR | Project/site code — Solar + BESS site
Discipline | 3-letter discipline code (see table below)
Doc Type | 3-4 letter document type code (see table below)
Sequence | 4-digit running number, unique per document
Discipline Codes
Code | Discipline
CIV | Civil
ELE | Electrical
MEC | Mechanical
INC | Instrumentation & Control
HSE | HSE
QAC | QA/QC
PRO | Procurement
PMT | Project Management
Status Codes
Code | Meaning | Typical Next Step
IFR | Issued for Review | Internal / discipline lead review
IFA | Issued for Approval | Sent to client/consultant for formal approval
IFC | Issued for Construction | Released to site for execution
AFC | Approved for Construction | Approved, no further comments expected
AB | As-Built | Final closeout after construction/installation
REJ | Returned with Comments | Requires revision and re-submission
How to Use This Register
1. Add a new row on the MDR sheet for every new document; follow the numbering convention above.
2. Update the Status and Rev columns as the document moves through review/approval — a dropdown is enabled on the Status column.
3. The Dashboard sheet recalculates automatically — no manual counting needed.
4. Link every submission/approval action to a Transmittal Ref (see Project 2: Transmittal Log).
5. Log major revision changes for key documents on the 'Revision History (Sample)' sheet.