## Transmittal Log
TRANSMITTAL LOG
Project: 50 MW Solar PV Plant with 20 MWh BESS ¦ VoltSun Labs (RJ Corp Group) ¦ Document Controller: [Your Name]
Cross-referenced to Master Document Register (MDR) — Transmittal Ref column ¦ Log updated as of: 21-Aug-2026
S.No | Transmittal No. | Date Issued | From | To | Purpose | Documents Included | Rev | Response Required By | Status | Days Open | Remarks
1 | TR-0001 | 2026-05-13 | VoltSun Labs - Engineering | Client Consultant | For Review | VSL-SLR-CIV-DRG-0001 - Site Grading & Levelling Plan; VSL-SLR-CIV-DRG-0002 - Module Table Foundation Layout; VSL-SLR-CIV-DRG-0003 - Pile Foundation Design - Zone A | - | 2026-05-20 | Overdue | 100 | Response pending - follow up required
2 | TR-0002 | 2026-05-25 | VoltSun Labs - Engineering | Client / PMO | For Approval | VSL-SLR-CIV-DRG-0004 - Inverter/BESS Plinth Foundation Design; VSL-SLR-CIV-RPT-0005 - Soil Investigation Report; VSL-SLR-CIV-DRG-0006 - Internal Road & Drainage Layout | - | 2026-06-04 | Closed | 10 | Response received and logged in MDR
3 | TR-0003 | 2026-06-06 | VoltSun Labs - PMO | Site Construction Team | For Information | VSL-SLR-CIV-BOQ-0007 - Civil Works BOQ - Zone A & B; VSL-SLR-ELE-DRG-0008 - Plant Single Line Diagram (SLD); VSL-SLR-ELE-DRG-0009 - MV Cable Schedule - Zone A | - | 2026-06-16 | Closed | 10 | Response received and logged in MDR
4 | TR-0004 | 2026-06-18 | Client Consultant | VoltSun Labs - Engineering | For Construction | VSL-SLR-ELE-DRG-0010 - Earthing & Lightning Protection Layout; VSL-SLR-ELE-DRG-0011 - DC Cable Routing Layout; VSL-SLR-ELE-DRG-0012 - Inverter Room Electrical Schematic | - | 2026-06-28 | Open | 64 | Awaiting response within due date
5 | TR-0005 | 2026-06-30 | VoltSun Labs - Engineering | Client Consultant | For Review | VSL-SLR-ELE-SPEC-0013 - 33kV Switchgear Technical Specification; VSL-SLR-ELE-DRG-0014 - BESS Container SLD; VSL-SLR-ELE-CALC-0015 - Voltage Drop & Cable Sizing Calculation | - | 2026-07-07 | Closed | 7 | Response received and logged in MDR
6 | TR-0006 | 2026-07-12 | VoltSun Labs - Engineering | Client / PMO | For Approval | VSL-SLR-MEC-DRG-0016 - Module Mounting Structure - GA Drawing; VSL-SLR-MEC-CALC-0017 - Wind Load & Structural Calculation; VSL-SLR-MEC-SPEC-0018 - Tracker Mounting Structure Specification | - | 2026-07-22 | Overdue | 40 | Response pending - follow up required
7 | TR-0007 | 2026-07-24 | VoltSun Labs - PMO | Site Construction Team | For Information | VSL-SLR-MEC-DRG-0019 - BESS HVAC & Fire Suppression P&ID; VSL-SLR-INC-DRG-0020 - SCADA Network Architecture Diagram; VSL-SLR-INC-SPEC-0021 - Weather Station Instrumentation Spec | - | 2026-08-03 | Open | 28 | Awaiting response within due date
8 | TR-0008 | 2026-07-28 | Client Consultant | VoltSun Labs - Engineering | For Construction | VSL-SLR-INC-DRG-0022 - PLC I/O List - Inverter Station; VSL-SLR-HSE-PLN-0023 - Project HSE Management Plan; VSL-SLR-HSE-PLN-0024 - Emergency Response & Evacuation Plan | - | 2026-08-07 | Closed | 10 | Response received and logged in MDR
9 | TR-0009 | 2026-05-19 | VoltSun Labs - Engineering | Client Consultant | For Review | VSL-SLR-HSE-PRC-0025 - Working at Height Procedure; VSL-SLR-HSE-PRC-0026 - Lifting & Rigging Safety Procedure; VSL-SLR-QAC-PLN-0027 - Project Quality Assurance Plan | - | 2026-05-26 | Closed | 7 | Response received and logged in MDR
10 | TR-0010 | 2026-05-31 | VoltSun Labs - Engineering | Client / PMO | For Approval | VSL-SLR-QAC-ITP-0028 - ITP - Module Mounting Structure; VSL-SLR-QAC-ITP-0029 - ITP - Cable Laying & Termination; VSL-SLR-QAC-RPT-0030 - Factory Acceptance Test Report - Inverters | - | 2026-06-10 | Open | 82 | Awaiting response within due date
11 | TR-0011 | 2026-06-12 | VoltSun Labs - PMO | Site Construction Team | For Information | VSL-SLR-PRO-BOQ-0031 - Procurement BOQ - Electrical Package; VSL-SLR-PRO-SPEC-0032 - Module Supply Technical Specification; VSL-SLR-PRO-SPEC-0033 - BESS Container Technical Specification | - | 2026-06-22 | Overdue | 70 | Response pending - follow up required
12 | TR-0012 | 2026-06-24 | Client Consultant | VoltSun Labs - Engineering | For Construction | VSL-SLR-PMT-PLN-0034 - Project Execution Plan; VSL-SLR-PMT-PLN-0035 - Project Schedule (Level 3); VSL-SLR-PMT-PRC-0036 - Document Control Procedure | - | 2026-07-04 | Closed | 10 | Response received and logged in MDR
13 | TR-0013 | 2026-06-28 | VoltSun Labs - Engineering | Client Consultant | For Review | VSL-SLR-PMT-RPT-0037 - Monthly Progress Report - Template | - | 2026-07-05 | Open | 54 | Awaiting response within due date

## Dashboard
TRANSMITTAL STATUS DASHBOARD
Live summary — pulls automatically from the Transmittal Log sheet
Total Transmittals |  | 13
Closed |  | 6
Open (within due date) |  | 4
Overdue |  | 3
Status Breakdown
Status | Count
Open | 4
Closed | 6
Overdue | 3
Transmittals by Purpose
Purpose | Count
For Review | 4
For Approval | 3
For Information | 3
For Construction | 3

## Sample Submission Cycle
SAMPLE DOCUMENT SUBMISSION CYCLE
Document: VSL-SLR-ELE-DRG-0008 — Plant Single Line Diagram (SLD) ¦ Full cycle from first issue to construction release
Transmittal No. | Date | From | To | Rev | Action / Outcome
TR-0003-A | 05-May-26 | VoltSun Labs - Engineering | Client Consultant | A | SLD issued for review — first submission alongside 2 other Electrical drawings in the same transmittal group.
TR-C-0001 | 12-May-26 | Client Consultant | VoltSun Labs - Engineering | A | Client returns transmittal with comments — tap-setting query on the transformer schematic. Status logged as Returned with Comments (REJ) in the MDR.
TR-0003-B | 20-May-26 | VoltSun Labs - Engineering | Client Consultant | C | Revised SLD re-issued for formal approval after incorporating comments. Rev advances from A (draft) to C (issued for approval).
TR-C-0002 | 02-Jun-26 | Client Consultant | VoltSun Labs - Engineering | C | Client returns transmittal with formal approval — no further comments. Document Controller updates MDR status to Issued for Construction (IFC), Rev 0.
TR-0004 | 03-Jun-26 | VoltSun Labs - PMO | Site Construction Team | 0 | Approved Rev 0 distributed to site via internal transmittal for construction release.
Note:
TR-0003 covers the outgoing submission and re-submission (grouped under one reference, suffixed -A/-B for each issue); TR-C-#### references are incoming transmittals received from the client. This mirrors how Aconex/ProjectWise separate outgoing and incoming transmittal numbering while keeping both linked to the same document.

## Legend & Template
LEGEND, BLANK TEMPLATE & HOW TO USE
Transmittal Numbering
TR-<SEQUENCE> (outgoing, from VoltSun Labs) ¦ TR-C-<SEQUENCE> (incoming, from client/consultant)
Purpose Codes | Meaning
For Review | Recipient reviews and returns comments; not yet a formal approval request.
For Approval | Formal submission requiring sign-off before the document can proceed to IFC/AFC.
For Information | Shared for awareness only; no response or action required.
For Construction | Approved document released to site for execution.
Status Definitions
Status | Definition
Open | Within the response due date; awaiting recipient action.
Closed | Response received and logged; documents updated in the MDR accordingly.
Overdue | Past the response due date with no reply — requires Document Controller follow-up.
Blank Transmittal Cover Sheet (copy for manual use)
Transmittal No.
Date Issued
From
To
Project | 50 MW Solar PV Plant with 20 MWh BESS
Purpose | For Review / For Approval / For Information / For Construction
Documents Included | (Doc No. — Title — Rev, one per line)
Response Required By
Prepared By | [Your Name], Document Controller
How to Use This Log
1. Every document leaving or entering the project is logged as a transmittal — never sent as a standalone email attachment.
2. Group related documents under one transmittal where they are issued together (see Transmittal Log sheet).
3. The Transmittal Ref recorded here matches the 'Transmittal Ref' column in the Master Document Register (Project 1) — cross-check both when updating status.
4. Update Status to Closed as soon as a response is logged; the Dashboard recalculates automatically.
5. Review the log weekly and flag anything Overdue to the Project Head / PMO per the Document Control Procedure (Project 3).